## Sheet1
Sub-System | Task | Dependant Tasks | Assigned To | Status | Notes
Gps | 1)Serial connection to Pi | - | Orestis Keisoglu | Done | Connect GPS to the Pi serially
| 2)Testing | 1) and 2) | Victor Emmanuel Meimaris & Ores. | Done | Test GPS accuracy and ensure data is being sent correctly to the flight controller
| 3)API Integration | All the above | John Zikos & Victor Meimaris | Almost done | Integrate GPS to the API to extract raw coordinates for debugging
| 4)Documentation | All the above | - | Not Done | Document all gps settings
Camera | 1)Serial connection to Pi | - | Orestis Keisoglu | Done | Connect Camera to the Pi serially
| 2)Data extraction for image analysis | 1) | - | Not Done | Extract images from video and send them to the API automatically
| 3)API Integration, analysis with AI | All the above | - | Not Done | Integrate camera to the API and analyse images with AI models
| 4)Documentation | All the above | - | Not Done | Document all camera settings
Flight Controller | 1)Serial connection to Pi | - | Georgios Georgitzikis | Done | Connect flight controller to the Pi serially
| 2)Firmware Setup | 1) | Georgios Georgitzikis | Done | Install ArduPilot firmware
| 3)Hardware Configuration | 1) and 2) | Victor Emmanuel Meimaris | Not Done | Configure and test ESCs, motors, and servos
| 4)Sensor Calibration | 1) and 2) | - | Not Done | Perform accelerometer, gyroscope,barometer and compass calibration & Verify GPS lock and accuracy
| 5)Auto Flight Mode Setup | 1) and 2) | - | Not Done | Configure and test flight mode
| 6)Parameter Tuning | 1) and 2) | - | Not Done | Adjust PID gains for stable flight, tune throttle response and altitude hold parameters & set failsafe parameters
| 7)Safety Checks | All the above | - | Not Done | Configure and test Return-to-Launch (RTL), set up geofencing and test failsafe behaviours
| 8)Data transmission | All the above | - | Not Done | Data transmission to and from API as well as ardupilot apps
| 9)Documentation and Testing | All the above | - | Not Done | Document and test all configuration and parameter settings
API | 1)Create prototype API server | - | Victor Emmanuel Meimaris | Done | Created prototype for testing A.I models early on
| 2)Create running API server on Pi | - | John Zikos | Done | Server for communicating remotely to send to and receive information as well updates and commands
| 3)Create running API for pc/laptop | - | John Zikos | Done | Server for communicating remotely to send to and receive information as well updates and commands
Design | 1)Wings | - | Michalis Christogiannopoulos | Almost Done | Prototype has been designed, testing is needed
| 2)Fuselage | - | Michalis Christogiannopoulos | Not Done | Fuselage is being designed
| 3)Tail | - | Orestis Keisoglu | Not Done | Tail is being designed